## Design
Job | Done By | Finish By
Finalize rear suspension, fix clearances | Orion | Jan 6th
ARB Geometry + Mount Locations | Orion | Jan 6th
Finalize Steering Geometry | Orion | Jan 6th
Update Design Spreadsheet | Orion | Jan 6th
Update Adams Model | Orion | Jan 6th
A-Arms Final CAD | Will | Jan 6th
Shock Cover Design | Orion | Jan 6th
Steering System Final CAD | Orion | Jan 6th
Front ARB Final CAD | Orion | Jan 6th
Rear ARB Final CAD | Orion | Jan 6th
Front Bellcrank Initial CAD | Orion | Jan 6th
Front Bellcrank FEA | Orion | Jan 6th
Front Bellcrank Final CAD | Orion | Jan 6th
Rear Bellcrank Initial CAD | Will | Jan 6th
Rear Bellcrank FEA | Will | Jan 6th
Rear Bellcrank Final CAD | Will | Jan 6th
Front Upright Initial CAD | Ryan | Jan 6th
Front Upright FEA | Ryan | Jan 6th
Front Upright Final CAD | Ryan | Jan 6th
Rear Hub Initial CAD | Matt | Jan 6th
Rear Hub FEA | Matt | Jan 6th
Rear Hub Final CAD | Matt | Jan 6th
Front Hub Initial CAD | JP | Jan 6th
Front Hub FEA | JP | Jan 6th
Front Hub Final CAD | JP | Jan 6th
Wheel Assembly/Center CAD | Orion | Jan 6th
A-Arm Mount Block CAD | Orion | Jan 6th

## Parts - Ours
Part | Quantity | Job | Done With | Material Needed | Done By | Finished By
Uprights Rear | 2 | Write CAM | CNC | 4.5" Blocks
Pre-Machine
Run CAM
Post-Machine
ARB Mounts | 4 | Write CAM | CNC | 1/2" Plate
Run CAM
Post-Machine
Steering Column Mounts | 3 | Write CAM | CNC | 1/2" Plate
Run CAM
Post-Machine
A-Arm Jig | 1 |  | Mill | 4.5" Block
Steering Column Tubes | 1 |  | Lathe | 5/8,3/4" Tube 1020 |  | Jan 4th.
U-Joints Trim |  |  | Mill | No
Steering Rack Spacers | 2 |  | Lathe | No |  | Jan 4th.
ARB's | 2 |  | Lathe | 5/8" Tube 1020 |  | Jan 4th.
A-Arm Notch + Weld | 8 |  | Manual Mill | 5/8 Tube 1020
Rod End Cone Spacers | 24 |  | Lathe | Barstock AL 1/2"
Shock Cover Mold | 1 | Write CAM | CNC | Machinable Foam
Run CAM
Uprights Rear | 2 | Write CAM | CNC | 4.5" Blocks
Pre-Machine
Run CAM
Post-Machine

## Parts - Sponsors
Part | Quantity | Done With | Material Needed | Done By | Finished By
Uprights Rear | 2 | CNC | 4.5" Blocks | APT
Hubs Rear | 2 | CNC | Yes | APT
Hubs Front | 2 | CNC | Yes | APT
Bellcranks Rear | 2 | CNC
Bellcranks Front | 2 | CNC
Frame Mount Blocks | 16 | CNC |  | Musashi?
Upright Mount Blocks | 2 | CNC |  | Musashi?
ARB Tabs | 8 | Laser Cut | Sheet Steel ___ | NPL
Camber Shims 1/8" | 14 | Laser Cut | Sheet Steel 1/8" | NPL
Camber Shims 1/16" | 6 | Laser Cut | Sheet Steel 1/16" | NPL
A-Arm Gussets/Plates | 8 | Laser Cut | Sheet Steel ___ | NPL
A-Arm Bearing Cups | 24 | Lathe | Barstock Steel 1"
Hub Washers | 2 | Lathe
Susp. Link Ends | 12 |  | Lathe | Barstock Steel 5/8"

## Parts - Ordered
Part | Quantity | Supplier | Ordered Date
Springs - Hyperco | 12 | Essex Parts
U-Joints | 20 | Summit Racing
Studs | 20 | Summit Racing
Lugs | 20 | Summit Racing
ARB Bushings | 12 | Igus Bearings
5/8 Tubing |  | Metal Supermarkets
Upright Ball Bearings | 8 | SKF
Spherical Bearings | 24 | SKF
Fasteners |  | Fastenal
Springs Pins | 5 | Fastenal

## Tuning
Job | Done By | Finish By